## Task 2a
Task 2a
|  | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20
Task a | Explore market for new product | bar: week 1 to week 3
Task b | Develop concept for new product | bar: week 4 to week 7
Task c | Talk to suppliers for materials | bar: week 8 to week 9
Task d | Order tooling for new project | bar: week 10 to week 12
Task e | Train production staff | bar: week 13
Task f | Test run for new product production | bar: week 14
Task g | Develop packaging for new product | bar: week 15 to week 16
Task h | Develop advertising material for new product | bar: week 17 to week 18
Task i | Give presentations to potential buyers of new product | bar: week 19

## Task 2b
Task 2b
|  | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20
Task a | Explore market for new product | bar: week 1 to week 3
Task b | Develop concept for new product | bar: week 4 to week 7
Task c | Talk to suppliers for materials | bar: week 8 to week 9
Task d | Order tooling for new project | bar: week 8 to week 10
Task e | Train production staff | bar: week 11
Task f | Test run for new product production | bar: week 12
Task g | Develop packaging for new product | bar: week 13 to week 14
Task h | Develop advertising material for new product | bar: week 13 to week 14
Task i | Give presentations to potential buyers of new product | bar: week 15

## Task 3b
Task 3b
|  | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22 | week 23 | week 24 | week 25 | week 26 | week 27 | week 28 | week 29 | week 30 | week 31 | week 32 | week 33 | week 34 | week 35 | week 36 | week 37 | week 38 | week 39 | week 40 | week 41 | week 42 | week 43 | week 44 | week 45 | week 46 | week 47 | week 48 | week 49 | week 50 | week 51 | week 52
Task a | Write proposal
Task b | Feasibility study
Task c | Investigation and analysis
Task d | Requirements specification
Task e | Design phase
Task f | Design review and signoff
Task g | Development phase
Task h | Testing
Task i | Implementation of new system
Task j | Staff training on new system
Task k | Signoff of new system
Task l | System goes live